## Slide 1
Laporan Kemajuan Projek
myWAP
Timeline pembangunan, status semasa, dan pelan penyelesaian bayaran sebelum muktamar September 2026.
Status Ringkas
• Pembangunan web apps telah siap dari sudut fungsi utama.
• Fasa semasa tertumpu kepada minor polish, testing dan deployment readiness.
• Fasa seterusnya ialah setup native apps dan submission ke App Store serta Play Store.
Tarikh mula projek
14 Mei 2026
Status setakat
4 Ogos 2026
Nilai projek
RM35,200
Bayaran diterima
RM13,866.67
Baki semasa
RM21,333.33
Disediakan untuk semakan pihak pengurusan dan penjadualan kutipan sebelum muktamar.

## Slide 2
Timeline Projek Berdasarkan Modul Sebenar
Audit dibuat daripada struktur modul, routes, controllers, pages Vue dan dokumen status projek.
Pecahan Modul
• Auth, OTP, onboarding & profile
• Member card, directory & transition
• Events, QR attendance & usrah
• Infaq, yuran, finance dashboard
• Products, orders & referral system
• Broadcast, polls, popups & content hub
14-31 Mei
1-15 Jun
16-30 Jun
1-15 Jul
16-31 Jul
1 Ogos - 9 Sep
Asas sistem
Setup stack, DB, role & organisasi
Core membership
Register, OTP, profile, card, directory
Member modules
Announcements, library, events, usrah, infaq
Commerce & engagement
Products, referral, polls, video, popup
Admin & finance
Import ahli, yuran, laporan, dashboard
Finalisation web
QA, bug fixing, polish, testing
Native apps
Setup wrapper, packaging, store submission
Rumusan status
Web apps telah siap dari segi fungsi utama. Tempoh semasa digunakan untuk minor polish dan testing, manakala minggu berikutnya difokuskan kepada native app setup, packaging, dan submission ke App Store serta Play Store sebelum buffer semakan muktamar.

## Slide 3
Status Bayaran dan Cadangan Ansuran
Pecahan semasa menunjukkan baki RM21,333.33 yang dicadangkan selesai sebelum muktamar September 2026.
Ringkasan Kewangan
Nilai Projek
RM35,200.00
Bayaran Diterima
RM13,866.67
Baki Semasa
RM21,333.33
Kemajuan Bayaran Mengikut Pihak
WADAH
Jumlah: RM17,600.00
Telah dibayar: RM10,000.00
Baki: RM7,600.00
ABIM
Jumlah: RM14,080.00
Telah dibayar: RM2,346.67
Baki: RM11,733.33
PKPIM
Jumlah: RM3,520.00
Telah dibayar: RM1,520.00
Baki: RM2,000.00
Cadangan Jadual Ansuran Sebelum Muktamar
Tarikh
Pihak
Cadangan Bayaran
Rasional
15 Ogos 2026
WADAH
RM7,600.00
Menjelaskan baki selepas web apps siap dan native setup bermula
22 Ogos 2026
PKPIM
RM2,000.00
Menyelesaikan baki semasa fasa build dan packaging
31 Ogos 2026
ABIM
RM5,866.67
Bayaran pertama sebelum submission store selesai
7 September 2026
ABIM
RM5,866.66
Bayaran akhir sebelum buffer muktamar